## Sheet1
Meeting Date | Meeting Time | Meeting Place | People who attended | Discussions | Outcomes | Meeting Duration
Feb 16,2024 | 7:00 pm to 8:30 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | 1.Team introduction. 2.Project discussion 3. How to start with the sprint1 4.Task distribution 5.Topic Finalisation | Sprint 1 was initiated, tasks were distributed among team members and the topic - "Hospitality Industry" was finalised. | 90 minutes
Feb 23,2024 | 7:00 pm to 8:30 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | 1. Discussion around research for topic and shared ideas. 2. finalised the entities and distributed entities to work on amongst team members. | Research topics were explored, ideas were exchanged, and the project entities were finalized and assigned to team members for further development. | 90 minutes
Feb 24,2024 | 7:00 pm to 8:30 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | 1. Discussion about the summary based on the tabular structure created by all. 2. Developing the ER Diagram and then finding the trap to get the Final_ERD. | Summarised the research performed in a collaborative tabular structure, an ER Diagram was developed, and potential issues were addressed, resulting in the final ERD. | 90 minutes
Feb 27,2024 | 9:00 pm to 10:00 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | 1. Finalising Sprint 1 and group deliverables | Finalised Sprint 1 tasks and deliverables and submitted the Report (Sprint 1). | 60 minutes
Mar 9,2024 | 11:00 am to 11:30 am | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Sprint 2 discussion , analysis and task distribution | The Sprint 2 was initiated, analysed and allocated tasks among team members. | 30 minutes
Mar 11,2024 | 5:30pm to 6:00 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Discussion with Head TA on team progress and concerns | Upon receiving feedback from HeadTA, increased the number of entities. | 30 minutes
Mar 11,2024 | 6:00 pm to 7:00 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Creating ddls for sprint 2 , also discussion around database fragmentation | DDL commands were created, Finalised "Database - level Fragmentation" and made some discussions regarding it. | 60 minutes
Mar 12,2024 | 9:30 pm to 10:00 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Progress Discussion call | Discussed on each team member's progress on the assigned tasks. | 30 minutes
Mar 13,2024 | 6:00 pm to 8:00 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Report finalisation for sprint 2, Codebase for GDC handling to fetch db server dynamically based on data catalog, testing of code. | The report for Sprint 2 was finalized, the codebase was adapted to handle GDC requirements for dynamic database server fetching, and code testing was completed. | 120 minutes
Mar 13,2024 | 10:00 am to 10:30 am | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Meeting with Professor regarding doubts . | Clarifications were obtained from the Professor regarding Fragmentation and GDC | 30 minutes
Mar 22,2024 | 5:30pm to 5:45pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Meeting with HeadTA for Final Project Q&A. | Project Q&A session with HeadTA. | 15 minutes
Mar 26,2024 | 6:10pm to 6:40 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Worked on Preparing the Final Report. | 70% Completion of Final Report. | 30 minutes
Mar 27,2024 | 6:00pm to 6:40 pm | Online | Himanshi verma, Poojitha Mummadi, Jay J Patel, Bhavya Dave | Finalising Report and Deliverables. | The project report and deliverables were finalised and completed, marking the end of project. | 40 minutes